## Cover page
Event Management Plan
This resource has been created to assist event organisers with the development and management of their event.
In this spreadsheet you will find information regarding permits and applications that may be required for your event, as well as some useful templates for budgeting, marketing, risk and emergency management.
Tips
1. Each sheet contains a 'how to' explanation to assist you in completing the worksheet
2. Complete the 'Event Details' page first, this will then pre-populate key information into other worksheets
3. You can print each sheet to use and distribute to stakeholders at your event

## Event Details
Event Details
Fill in your event details below, this information will then pre-populate onto the other tabs
Event Name:
Event Location:
Event Date:
Start and Finish Times (e.g. 4pm - 12 midnight):
Expected Attendance Numbers:
Target Group:
Key Personnel | Name | Telephone
Event Manager/Coordinator
Safety Officer
Secretary
Security Officer
Volunteer Coordinator

## Key Contacts
Key Contacts
Add or delete organisations and contact details to suit your event
| Position/Organisation | Name | Telephone
Event Manager/Coordinator
Safety Officer
Secretary
Security Officer
Volunteer Coordinator
Area Warden 1
Area Warden 2
Area Warden 3
| Mildura Rural City Council |  | 5018 8100
| Victoria Police |  | 000
| Ambulance |  | 000
| SES |  | 13 25 00
| Vic Roads |  | 13 11 71
| CFA |  | 000
Taxi
| Poisons Information |  | 13 11 26
Plumbing
Electrician

## Permits and Applications
Permits and Applications Schedule
Below is a list of applications and permits that may be required for your event. Click on the corresponding links to find out further information
Application or Approval |  | Required | Due date for Application or Lodgement | Lodged | Date | Lodgement details
Venue Hire Application Form | [5 empty] | Click to complete venue hire application form
Events Funding and Support | [5 empty] | Click for more information
OneMusic Licence | [5 empty] | Click to apply for OneMusic Licence
Liquor Licence (Select Licence Type) : | [5 empty] | Click to apply for a Liquor Licence with VCGLR
Risk Management Plan | [5 empty] | Complete Risk Management tab
Emergency Management Plan | [5 empty] | Complete Emergency Management tab
COVIDSafe Event Plan | [5 empty] | Complete COVIDSafe Event Plan tab
Festivals and Events - Food Providers List | [5 empty] | Click to download form
Planning Permit Application Form | [5 empty] | Click to download form
Legend
|  | Lodgement Status | Warning Colour
Lodged
7 days or less
14 days or less
21 days or less
Yes
No
N/A
| Major Event Licence | #VALUE!
| Limited Licence | #VALUE!

## Budget
Operating Budget
The following template is provided as an example and should be adapted to suit your event
|  | EXPECTED TOTAL SURPLUS / LOSS | ACTUAL TOTAL SURPLUS / LOSS
|  | 0 | 0
INCOME
DESCRIPTION |  | EXPECTED $ | ACTUAL $ | NOTES
Ticket Sales
Sponsorship
Grants
Raffles & Fundraising
Stall Fees
TOTAL INCOME |  | 0 | 0
EXPENSES
DESCRIPTION |  | EXPECTED $ | ACTUAL $ | NOTES
VENUE HIRE | SUBTOTALS | 0 | 0
Hire Fee
INFRASTRUCTURE | SUBTOTALS | 0 | 0
Equipment Hire
Audio Visual
Traffic Management
First Aid
Toilets
Power
Security
Waste Management
PROGRAM | SUBTOTALS | 0 | 0
Entertainment
Travel & Accommodation
Firworks/Pyrotechnics
CATERING | SUBTOTALS | 0 | 0
Food/Water for Staff/Volunteers
Food for performers
MARKETING | SUBTOTALS | 0 | 0
Design Work
Print Advertising
Television
Radio
Event Program
Flyers
Postage and Distribution
Signage
Photography
Media Launch
ADMINISTRATION | SUBTOTALS | 0 | 0
Permit Fees
Salaries and Expenses
Stationery
Decorations
Prizes
Insurance
Contingency
TOTAL EXPENSES |  | 0 | 0

## Action Plan
Action Plan
The following template is provided as an example and should be adapted to suit your event
[9 empty] | Due Date |  |  |  | Started |  |  |  | Completed
| Planning Category | Start Month | Actions Required | Who | Due Date | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | Notes
[6 empty] | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
| Entertainment | July | Book family entertainment | John Smith | 2020-07-13 | bar: July 13
| Safety | July | Book safety officer | Chris Jones | 2020-07-20 | bar: July 20
| Risk Management | August | Complete Risk Plan | John Smith | 2020-08-03 | [17 empty] | Work with safety officer | bar: August 3

## Run Sheet
Run Sheet
Order of Proceedings
| Time | Task/Action | Who
| 6.00am | Vendors bump in | Vendors
| 7.00am | Vendor vehicles to be removed from site | Vendors
| 7.00am | Site set up | Event staff
| 8.00am | Acknowledgement of country | MC
| 8.10am | Housekeeping, amenities, entertainment | MC
| 8.15am | Band to play on stage | Band
| 8.45am | Thank band for performance | MC
| 8.50am | Registrations open | Event staff
| 9.30am | Registrations close | Event staff
| 9.30am | Morning tea served | Vendor x
| 10.00am | Ceremony commences | MC

## Marketing Plan
Event Marketing Plan
The following marketing template is a guide for event organisers. You can edit it to suit your own needs and incorporate your own information. Delete the sample answers (in italics) and any sections or areas not applicable to your event.
1. Key Event Marketing Goals
Outline the key goals of the event marketing plan. Include specific goals and be specific as possible with actual targets.
• Attract at least 3,000 people to the event from within Mildura municipality and southern NSW and northern Victoria. o Achieve at least 50% return visitation (i.e. visitors from previous 3 events). o Encourage people to stay an average of 2 nights in the Mildura region. • Increase attendance at our event by 20% on previous year (from 1,000 to 1,200). o Increase participation in our sport/art/cause/charity throughout the year by at least 20%. o Generate greater community and business awareness leading to at least 2 new sponsors. • Increase ticket sales by 500 (from previous year) by increasing the number of new people attending our event. o Generate greater awareness of our sport/art/venue o Broaden the type of people attending our event, with a particular focus on people who are not currently engaged with our activity/specific age groups etc. o Promote the assets of Mildura to people outside the municipality.
2. Key Target Audiences
Describe the people you want to attract to your event. Identify your primary target audiences (i.e. the main group of people you want to attract) and your secondary target audience (the second most important group of people you want to attract). Describe your audiences in as much detail as you can. E.g. age, gender, where they are from, what they like, job type, income brackets, what they read/listen to/watch/engage with etc.
Primary target audience: • People who currently compete in our sport/activity/special interest area. The majority are aged from 18 – 55 years, 60% men, 40% women, from Mildura, southern NSW and northern Victoria (within a 3 hour radius of Mildura), most have a passion for water sport, many are in trades with their own business. Secondary target audience: • People who have not previously completed in our event (or possibly other events) but are currently active water sport enthusiasts. They include people from Melbourne and regional locations across Victoria and NSW, own a boat and currently water ski recreationally.
3. Key Messages and Brand
Identify your event branding and the key messages you will use consistently across your marketing campaign. The brand is the visual image or identity you project to your key target markets. Messages include both motivational (why people should attend) and informational (e.g. a change in parking arrangements, how to book accommodation etc).
Brand Examples: - The following name and logo will be used in our promotional campaign: - Our “by-line” will be “Great fun in the Sun!”. - The following images will be used to promote our event: (e.g. event image, Mildura image) Key Message Examples: - Date and venue - Specific messages - e.g. “Your only chance to be a part of the Guinness World Record breaking attempt to….” - Event will be a fun packed day for kids of all ages. - This year’s brand new feature will be…. - Book early as tickets are limited - Book your accommodation packages through our 1800 number…
4. Marketing Support and Partnerships
Outline your marketing support (e.g. organisations you have contracted) and any marketing or media partners. Examples may include website designers, social media experts, media sponsors, printing suppliers etc.
5. Key Stakeholder - Communication Plan
Identify all your key stakeholders (those impacted or likely to impact your event). Identify how, what, when and who will you communicate with them. They are likely to include Council, emergency services, affected businesses and residents, your event partners, tourism industry etc.
Stakeholder |  | What/Message |  |  | How |  | When |  | Who
Council |  | Obtain permits. Invite Mayor to…. |  |  | Monthly meetings |  | By July 1, 2017 |  | Sponsor coordiator
Sponsors |  | Approval for logo use etc. Keep up to date with event progress. Send invites to…. |  |  | Draft marketing material sent for approval. Set meetings |  | Nov 11, 2017 Dec 3, 2017 |  | Sponsor coordiator
Affected residents and businesses |  | Notify of road closures and traffic impacts. |  |  | Letter box drops |  | Dec 3, 2017 |  | Ops Manager
Tourism industry |  | Event dates – asap. Booking system and special offers on websites and promotional material. |  |  | Event info in Tourism Association newsletter. |  | By Sept 1, 2017 |  | Sponsor coordiator
Add stakeholders relevant to your event
5.1 Launches, announcements, public relations
Outline when and how you will do any launches, announcements, media or sponsor events or other public relations activities
5.2 Website and Digital Media
Outline your existing website traffic and your targets. Identify the key additions and changes to your website as you get closer to the event. Include how you will promote your event and the Mildura region if applicable.
Web Analytics - Examples
Analytic |  | Current Situation |  | Goal (by event date)
Sessions |  | 4000 |  | 8000
Users |  | 1500 |  | 2500
Page Reviews |  | 5000 |  | 7000
Website Plan - Examples
Activity |  |  |  | Date |  | Who
2017 event details added (2016 removed) |  |  |  | By June 30, 2016
Mobile friendly site activated
Sponsor links and special offers added
Tourism information included - links to VIC, MRT
Search Engine Optimisation (SEO)
New contact added (insert dates)
Set up analytics tool to measure
Special tourism and retail packages and offers
5.3 Social Media Plan
Outline your existing social media reach, how to build it and how to promote your event, the Mildura region, work with your event partners etc.
Hashtags:
Event Hashtags |  | Tourism Hashtags
#yourhashtag |  | #visitmildura
#visitthemurray
#visitvictoria
#newsouthwales
#seeaustralia
#holidayhere
Targets:
Analytic |  | Current Situation |  | Goal (by event date)
Current likes on Facebook |  | 20000 |  | 27000
Current Twitter followers |  | 4000 |  | 6000
Social Media Plan:
Date |  | Channel |  | Title |  | Content |  | Who
2016-12-01 |  | Facebook |  | Add BOOK NOW to Facebook - link bookings system
2017-01-01 |  | Facebook |  | Happy New Year from our event
2017-01-10 |  | Facebook |  | Feeling lucky? |  | Sponsor X is pleased to giveaway a $200 voucher to one lucky fan of our event. Share to win….(pic -sponsor
|  | Facebook Twitter |  | Share Mildura's secrets |  | Did you know Mildura has (interesting fact). Come along on (date) to the (event) and…..
5.4 Email Marketing
Outline the size and source of your email database, how you will grow it, and communicate with your database.
Database |  |  |  | Current Situation |  | Goal (by event date)
Past attendees |  |  |  | 2000 |  | 4000
Sponsors, partners, supporters, donors |  |  |  | 50 |  | 70
Other stakeholders |  |  |  | 600 |  | 2000
Email database will be expanded by:
- "Register to receive updates" to be added to website
- Competition to be run via social media with prize from key sponsor 16 - 12 weeks prior to event (emails required to enter)
- Competition at event with prize from sponsors
Email Marketing Campaign
Date |  | Campaign |  | Database |  | Who
2017-01-01 |  | Launch for 2017 |  | All 300 |  | TH
2017-02-01 |  | Competition |  | All 300, plus via sponsor and event partner emails
2017-03-01 |  | Special offer |  | All 300, plus via sponsor and event partner
5.5 Printed Collateral
Include details of printed collateral such as posters, fliers, newsletters etc
Collateral | By When | Distribution channels |  | Who |  | Cost
1000 x DL flyers (double sided) | Designed and printed by Jan 21, 2017 | Local retailers x 400 Mail database x 100 Visitor Centres x 500 (Mildura and Murray region) |  | Marketing Co-ordinator
70 x A2 Posters | As above | Local retailers x 40 Notice boards x 20 Visitor Centre x 5 |  | Marketing Co-ordinator
2,000 x Programs | By March 30, 2017 | Distributed at event |  | Marketing Co-ordinator
5.6 Advertising Plan
Outline your advertising plan. Adjust the table to suit your plan.
Advertising | Media | Location |  | When |  | Cost
Television adverts - 15 sec x 50 placements | WIN TV | Mildura, Shepparton, Western Victoria windows |  | 1/1/2017 - 15/1/2017
2 adverts for tickets sales - 3col x 129 | X Newspaper | Mildura |  | 15/1/2017 22/1/2017
Media Sponsorship Plan | Media | Location |  | When
Radio sponsorship - 100 x 30 sec adverts | Radio station AB | Murray region |  | 1/1/2017 - 21/1/2017
5.7 Media Plan (non-paid/editorial)
Outline your media plan including long term media (i.e magazines etc that can require up to 4 months lead time) and short term media. Consider interesting angles, new stories, photo opportunities, special announcements etc
Media Opportunity |  | Media |  | Location |  | When |  | Who
Announcement of new dates and changes |  | Local radio, newspaper, TV |  | Mildura and region |  | 2017-01-15
Feature story about event and Mildura |  | Our national magazine, 10,000 readers |  | Australia, New Zealand |  | Copy and pics by 20/1/2017. Story to run from 20/2/2017
Ticket sales and key attraction |  | Local radio, newspaper etc
Key Media Contacts
Identify key media contacts, who will make contact and how you will build relationships. Consider local, regional, state, national contact.
Name |  | Media |  | Story/Angle |  | Phone |  | Email
5.8 Marketing Partners Plan
Outline who else will promote your event and how this will happen.
Date |  | Marketing |  |  |  | Who |  | Information to be included
Motel A, B and C - to send out event details to their email database
Stallholders A, B, C, D to promote event on their social networks
Sponsors A, B, C to promote event on social networks and via email to their clients
Venue X to include posters at venue. 3 x social media posts in 5 weeks leading up to event
6. Marketing Activities
Decide which marketing tools you will use to promote your event. Below are examples of tools (there are likely to be other tools available to your event not listed). Select only the tools that will most effectively reach your target audiences, taking into consideration your expertise, resources and budget. Identify the timeframes, budget and expertise needed to implement each activity. Delete the table below when you have selected your tools.
MARKETING TOOLS |  |  |  | DIGITAL, ONLINE
Word of Mouth |  |  |  | Website
Identified ways to spread event via word of mouth |  |  |  | Update website
Databases/Direct mail |  |  |  | Social Media, Blogs, Forums
Mail and email addresses |  |  |  | Facebook, Twitter, YouTube, Instagram, LinkedIn etc
Loyalty/Return visitation program |  |  |  | Event Apps
Eg. Discounts, special offers, thank you cards |  |  |  | App or QR code for posters, adverts, fliers etc
Ticketing |  |  |  | On-line advertising
Selling methods, online, at events, sign up days etc |  |  |  | Google ads, Facebook etc
Signature |  |  |  | SMS
Include event details in email signatures |  |  |  | SMS updates,details etc
PUBLICITY/PUBLIC RELATIONS |  |  |  | On-line Calendar listings
Free Editorial |  |  |  | Event website calendars, Council, tourism operators
Editorial stories, pictures, listings etc |  |  |  | MARKETING MATERIALS
Launch |  |  |  | Marketing Material
Launch media, sponsors, stakeholders etc |  |  |  | Fliers, posters, programs etc and distribution plan
Functions |  |  |  | Signage; banners
Thank you functions, awards, welcome events etc |  |  |  | Signs on town entrances, other locations, venues
Guest speaking opportunities |  |  |  | Notice Boards/Letter box drops
Promote event at speaking engagements |  |  |  | Notices on notice boards; shops, letter box drops
Other Events/Promotions |  |  |  | Outdoor advertising
Attend other events, shopping centres etc |  |  |  | Buses, billboards, signage, banners
MEDIA - EDITORIAL, ADVERTISING |  |  |  | COMMUNICATIONS
Media Releases |  |  |  | Local Politicians
Determine topics, dates, distribution strategy |  |  |  | Request inclusion in newsletters, at office etc
Television |  |  |  | Council, Tourism, Businesses
Sponsorship, community service announcements, paid ads, news stories, interviews |  |  |  | Identify opportunities for advertising, promotions,special offers, cooperative marketing etc
Radio |  |  |  | Co-promoters
Sponsorship, community service announcements, paid ads, prize giveaways, joint sponsor promotions/adverts |  |  |  | Identify potential partners to promote event - e.g. sponsors, local businesses, tourism, retailers
Mazagines, Trade publications etc |  |  |  | EVALUATION
Media releases, stories, pictures, advertising |  |  |  | Media Clippings
What's On Event listings |  |  |  | Collate to use the following year and to evaluate marketing
Local, regional, state newspapers, mazagines etc
Newspapers
Sponsorship, advertising, media releases, prize giveaways, joint sponsor promotions/adverts
7. Calendar Listings and What's On Listings
Outline the websites and what's on listings (e.g. in magazines etc) you will add your event details to.
Website |  |  |  | When |  | Who
www.eventsmildura.com.au
http://www.visitthemurray.com.au
http://www.murrayriver.com.au/
www.visitvictoria.com
https://www.atdw-online.com.au/#/login
http://www.aroundyou.com.au/
8. Singage Plan
Outline the signage plan to promote the event
Signage |  | Location |  |  |  | Installation Dates |  | Who
9. Tourism Marketing Plan
Outline what you will do to market Mildura and the region as part of your marketing campaign
The event will highlight the key attributes of Mildura and reasons to visit including the following:
- Social media posts (4 in lead up to the event) will include information on Mildura, how to book accommodation and why stay an extra day. Currently 15,000 likes on Facebook page.
- Mildura Council & Mildura Regional Development have compiled a Destination Marketing Toolkit which includes a range of Mildura and Wentworth 'hero' images, social media template posts, a 30 second TVC and VisitMildura branding. These can be utilised for publications, websites or flyers to promote your event in the region. Please contact MRCC Events Team at events@mildura.vic.gov.au to access this free toolkit
- Event website will include the Mildura Visitor Information and Booking Centre phone numbers, email address and website (www.visitmildura.com.au) link on the front page and in our “How to book” page. Average website unique visitors is 2,000 per year.
- In partnership with 5 accommodation providers (list) the event will be marketed by emails to a database of 8,000 people who have previously visited Mildura or have expressed an interest in visiting. Event and tourism information will be included in the email.
- To attract new visitors to the event and Mildura, event will conduct an advertising program in Melbourne (via radio XX – 2 weeks x 100 15 sec adverts).
10. Outline other Marketing Tactics, Plans and Activities
11. Marketing Evaluation Plan
Outline how you will evaluate whether your plan has been successful. Identify any tools you will need to measure what worked and what didn’t work. These may include social media analytics, surveys (at event or on-line), feedback forms, ticket sales, phone calls/email enquiries/website traffic (following media/marketing activity), actual responses to special promotions, amount and type of media received, de-briefs etc.
12. Summary of Marketing Plan
You may wish to provide a summary of your marketing activities to ensure it aligns with key dates.
Example summary format 1:
Week/Date | Message/Activity |  | Website | Email | Media | Advertising | Signage | Printed
Flyers and posters printed
Media release issued
Program & early bird ticket announcement
Interview
Signage installed
Feature article; video
Special offer
Early bird closes Competition details
Detailed program
Interview/feature video
Special offer from sponsor
2 weeks to go - FAQ - preparing for event Why attend
Excitement building - media
Event Date
Post event thank you; survey, sponsor
Highlights and photos
Example summary format 2:
Activity | Who | Jan | Feb | Mar | Apr | May | June | July | Aug
Website |  | Develop | Live | Update | Update | Update | Update | Update | Update
Blog |  |  |  | Date | Attraction | Cost | Book | Why | Details
Email
Facebook
Twitter
YouTube
Media Sponsors |  | Approach | Approach | Negotiate | Agreement | Plan | Implement | Implement | Implement
Media Release |  |  |  | Entertainment |  | Annoucement | Attraction | x 3 | x 2
Print |  |  | Design | Design |  | Print | Distribution | Distribution | Distribution
Advertising
Signage
12. Marketing Budget
Identify all income and expenses associated with your Marketing Plan (add relevant line items to the sample template below). Create an excel spreadsheet and transfer to the Marketing Plan. Include your cash and in-kind income and expenditure
Item |  | Supplier |  | Cash Budget |  | In-kind Budget |  | Actual (YTD)
Income
Marketing budget |  | Festival |  | 5000 |  |  |  | 5000
In-kind sponsorship (actual documented value) |  | Radio Co |  | 0 |  | $3,000 |  | 0
|  | Printing Co |  |  |  | 1000
|  | Design Co |  |  |  | 500
|  | Social Media Co |  |  |  | 500
Cooperative advertising revenue |  | Tourism business |  | 500 |  | 500
Sponsorship |  | Council |  | 2000
|  | TOTAL |  | 7500 |  | 2500 |  | 5000
Expenditure
Design |  | Design Co |  |  |  | 500 |  | 500
Printing |  | Printing Co |  | 1000 |  | 1000
Website |  | Website Co |  | 500
Social Media |  | Social Media Co |  | 500 |  | 500
Signage |  |  |  | 1000
Advertising |  | Radio Co |  | 1000 |  | 3000
|  | Newspaper Co |  | 1000
|  | Magazine Co |  | 1000
|  | Tourism Mag |  | 500
Market research |  |  |  | 500
Photography |  |  |  | 500
|  | TOTAL |  | 7500 |  | 5000 |  | 500

## Risk Management
Risk Management Plan
HOW TO USE THIS TEMPLATE
Explanation
This document, when completed will provide you and other stakeholders with the information necessary to run a safe and successful event. All sections marked with an asterisk (*) are mandatory and must be completed. If a section of this form is not applicable to your event, enter NOT APPLICABLE. If this is your first time compiling an Event Risk Management Plan, this process will give you the opportunity to document all aspects of your event. If this has been done before, then information can be copied from previous years provided it is still relevant. If you require any assistance in completing your Event Risk Management Plan, please contact the Governance & Risk Unit on 5018 8100.
What is a Risk?
A risk is anything that threatens or limits the ability of an organisation (or Event Organiser) to achieve the successful running of the event.
What is Risk Management?
Risk management is a process of assessing all possible risks, problems or disasters before they happen and implementing controls to avoid or minimise the likelihood and consequence of the risks occurring.
Why do we need a Risk Management Plan?
There are a couple of key reasons why an Event Organiser needs to consider risk management for their event; to create an enjoyable experience for everyone, to ensure that no-one gets hurt and to minimise the chance or avoid being sued. Insurance is not a substitute for risk management
Event Planning Guide
If you are thinking about organising an event within the Mildura region, the Event Planning Guide is the best place to start. The guide highlights key considerations for event organisers including planning, running and promoting a professional, safe & successful event. The guide also contains a range of links to useful resources. A copy is available on Council’s website.
RISK ASSESSMENT PROCESS
Step 1 – Identify the Risks
A site visit prior to the event will help to identify potential risks, then thought should be given on ways to minimise them. You will be able to identify a number of risks, such as areas that need fencing off, inappropriate placement of proposed activities (i.e. trees overhead), or accessibility for emergency services to enter venue. Using Table 1: Examples of Hazards, Risks and Controls as a guide, fill in the Hazards/Sources and Risks columns by listing those relevant to your event in the Risk Assessment Template below.
Step 2 – Rate the Risks
A risk rating is determined by considering the likelihood and consequence of an incident occurring. Refer to Table 2: Risk Rating Matrix for definitions of each category, then fill in column 3 ‘Risk Rating’ of the Risk Assessment Template.
Step 3 – Identify Controls
To determine which controls will be implemented, consider what you are going to do to: • Reduce the likelihood of the risk happening; or • Reduce the consequences should the risk eventuate Fill in column 4 ‘Risk Controls’ of the Risk Assessment Template using the examples in Table 1 as a guide.
Step 4 – Rate the Risks with controls
Now determine the risk rating after taking into consideration the controls you identified in step 3. Fill in column 5 ‘Risk Rating’ of the Risk Assessment Template with your revised risk rating.
Step 5 – Control Responsibility
Nominate who will have ‘Responsibility’ in column 6 of the Risk Assessment Template. This person is responsible for ensuring the controls are implemented.
TABLE 1: EXAMPLES OF HAZARDS, RISKS AND CONTROLS
Planning a safe event
All reasonable care should be taken to ensure your event is safe for all involved. This applies to event staff, volunteers, performers, the audience and the public in surrounding areas. There are also resources online that are designed to assist Event Organisers to plan for safe events such as the free Worksafe publication: Advice for Managing Major Events Safely. The following table provides Event Organisers with examples of hazards / risks and corresponding control strategies that may be put in place for their event. This list is not exhaustive. As an Event Organiser, you should use these examples as a starting point in the risk assessment process. Discussion should then take place with other people involved in planning and delivering the event to identify other relevant hazards specific to the nature of your event.
Hazard / Source |  | Example Risks |  | Example Controls
Persons unfamiliar with the venue, event or co-workers |  | • Hazards not known • Slower reaction in an emergency |  | • Check with Council for known hazards and any past incidents • Check with people who have held the event in the past and/or past event debriefs • Communicate safety procedures to all stakeholders, including emergency procedures • Establish coordination / communication systems (e.g. meetings, email/sms groups, names and photos of key people on noticeboards) • Provide identifying badges or clothes for workers • Conduct training for employees, volunteers and contractors (Induction, Venue specific, Task specific, and Emergency Procedures)
Interaction with adjacent businesses, residents or events |  | • Traffic management • Fire • Noise • Fumes |  | • Check for other events that may impact on this event at planning stage (e.g. railway or roadworks that will impact on access) • Clarify whether the event will have exclusive/non-exclusive use of the venue. If non-exclusive, coordinate with other users • Consider how neighbouring residents, businesses and activities impact on this event
Persons become complacent in bump out phase |  | • Mental and physical fatigue • Time pressures to return venue to pre-event state • Bump out occurs at same time crowd is exiting • Many stakeholders recovering equipment simultaneously |  | • Roster personnel to manage fatigue • Roster personnel to supervise bump out phase • Establish realistic timeframes to return the venue to pre-event state in consultation with venue manager and other stakeholders • Plan timing and traffic management of bump out and retrieval of equipment so it does not conflict with exiting crowds
Structures, fences, stacked materials, etc collapsing |  | • Collapse of structures • Crushing injury to public or participants |  | • Structures constructed by staff or contractors with relevant qualifications • Structures erected according to building regulations • Use of materials with manufacturer’s specifications • Quantities of materials and fencing to be stacked flat to prevent collapse • Managers and staff monitor all structures
Cooking, candles, naked flame, hot surfaces |  | • Burn injury • Fire to start and be uncontrollable |  | • Stalls, food vendors and power supplies having dry chemical extinguishers and blankets at all risk areas • Access routes for emergency vehicles to be made available through event areas • BBQs to be guarded and out of public reach and fire contained so it can’t blow onto public • All hot surfaces and naked flame to be out of reach of public
Slip, Trip, Fall and Knock |  | • Bodily injury to public or participants |  | • Serious trip and fall hazards identified prior to event and removed or treated to prevent injury • Staff site safety induction • Cables installed overhead where possible • Rubber mats and cable traps over cables on ground • Barriers placed around protruding equipment • Changes in height and edges highlighted or barricaded • Slippery surfaces treated or isolated • Additional lighting in dark areas • Spills isolated then cleaned by crews as soon as reported
Weather |  | • Heat stress • Flooding • Fire • High Wind • Lightning • Falling trees or debris • Excessive sun exposure |  | • Set up electrical equipment so it is not exposed to rain or flooding • Determine contingency plans if there is a fire ban (e.g. cancel with appropriate communication, alter event (e.g. go indoors, do not use BBQs), continue with written permission from fire authority) • Monitor weather forecast and determine pre-event action if certain weather events occur or are likely • Provide shelter from sun and rain • Provide drinking water for patrons and workers • Provide weather appropriate clothing for workers • Hold the event at a time that will minimise risk of weather impact • Communicate weather related precautions that patrons should consider (e.g. bring a hat, sunburn cream, poncho) Consider selling / providing to patrons at the event. • Avoid placing vendors and activities near trees
Traffic Management |  | • Impact between pedestrians and vehicles or 2 vehicles |  | • Develop traffic management plan. Include: - Segregation of exiting pedestrians and bump out traffic - No go zones for certain locations or phases (e.g. no heavy equipment movement during event) - Liaise with public road authorities (e.g. VicRoads, Police) - Signage & Barriers - Parking and/or public transport options - Vehicle access accreditation - Staffing - Monitoring of conditions - Communication - Reduced speed limit
Crowd Control |  | • Overcrowding • Crushing (people pressed against object) • Incidents outside event boundaries |  | • Appropriate layout and space allocation • Allocated entry & exit routes • Provide clear queuing system • Provide timely information to patrons (e.g. signs, PA) • Provide sufficient workers to manage crowds
Alcohol & Illicit Drugs |  | • Negative consequences of intoxicated behaviour • Alcohol served to minors • Negative effects including dehydration, potential medical concerns, crowd disturbances or violence |  | • All service staff are RSA qualified • Plastic cups used in large-scale public events to lessen risk of injury and ensure compliance with liquor licensing • Safety notice in program about appropriate use of alcohol and attitudes to drink-driving • Reputable Security Company patrolling event for service compliance and inappropriate behaviour • Set up event site to avoid secluded areas where illicit drugs can be exchanged / consumed • Train personnel in recognising signs of illicit drug consumption and most appropriate response • Liquor in public place permit obtained • All bags are subject to search at the entrance
Live electrical wires or faulty equipment |  | • Electrocution hazard to patrons or performers • Unauthorised persons access electrical fittings • Contact with overhead wires |  | • Identify and communicate locations of overhead wires • All installations to be carried out by qualified electrical contractors • All leads and appliances to be tagged and tested • All electric’s to be installed in accordance with appropriate regulations • Temporary installations to run overhead where possible
Amusement Rides |  | • Clearance between rides, fixed structures and vegetation • Stability of the ride - firmness and slope of the ground and blocking of the ride • Poor maintenance • Poor training and operational procedures • Missing labels or warning signs • Poor location of fencing or barricades |  | • Provide adequate space for rides • Check ground is appropriate • Place in contract / hire agreement and confirm: - The ride has been maintained and set-up in accordance with the manufacturer’s instructions; - Check areas not readily visible to ensure proper maintenance has been undertaken; - Issues identified in the engineering assessment have been addressed; - All operators and supervisors have been trained; and - Adequate levels of supervision are available at all times
Manual Handling |  | • Sprains, strains, etc |  | • Minimise movement of material • Provide loading/unloading areas as close to final location of material as possible • Provide mechanical aides (e.g. forklift, trolley) • Provide sufficient people and time to carry out tasks
Contact with biological hazards |  | • Clean up body fluids • Sharps • Insects • Dogs / cats • Snakes |  | • Develop procedures for cleaning up body fluids and provide equipment and training • Provide sharps containers (fixed for patrons as appropriate and portable for workers with tongs and PPE) • Communicate to patrons rules for animals (e.g. no dogs / dogs on leads only, etc)
Evacuation areas |  | • Insufficient safe areas / evacuation zones |  | • Event Organiser to provide site map to all staff, volunteers and vendors • Sufficient space identified for evacuation site where there will be no infrastructure
Car parking |  | • Inadequate parking space |  | • Adequate provision reserved for car parking • Car parking managed by experienced external organisation
Food |  | • Food poisoning • Lack of food available |  | • Sufficient quantity of vendors sourced • All food vendors have food handling certificates • Copy of food vendors current public liability certificate • Food vendors have adequate refrigeration / cooling for their requirements • Adequate hand washing facilities have been provided for food vendors
Noise |  | • Disruption from sound of entertainment • Unable to communicate to patrons |  | • Have a backup system in place
Signage |  | • Ineffective signage |  | • Allow sufficient time for planning, proofing and production of signage • Use of reputable and certified company for printing and installation • All signage is secured and weighted
Children’s Activities/ Workshops |  | • Inappropriate or dangerous activity |  | • Activities run by professional organisation/staff • Parents informed they must supervise their own children at all times
Children |  | • Lost or missing children |  | • ID Wristbands at front entrance • Clearly marked Information Tent for lost children • Staff and volunteers briefed on lost children response plan
Communications |  | • Lack of effective communication onsite |  | • Use of two-ways and mobile phones • PA System / Megaphone onsite
Medical |  | • Ineffective, unprofessional personnel or service |  | • First Aid kit onsite for duration of event • St John Ambulance and/or off duty ambulance officer in attendance • Emergency contact numbers held by Event team • Egress maintained for First Aid vehicle and emergency vehicle to access First Aid treatment space • First Aid positioned in signed, accessible and central location onsite
Mosquitos |  | • Patron bitten by mosquito carrying mosquito-borne disease |  | • Have a repellent station set up • Display messaging around preventing bites • Changing the time of your event to avoid peek biting times
Amenities |  | • Insufficient amenities |  | • Supply of sufficient number of toilets for expected number of patrons • Clearly signed amenities and information about nearby alternative toilets • Cleaner contracted to clean and maintain toilets • Accessible toilets provided for people with limited mobility
Waste |  | • Insufficient waste disposal provisions |  | • Adequate quantity of bins placed throughout event • Dedicated cleaning staff allocated to monitor and clear bins
TABLE 2: Risk Rating Matrix
The Risk Rating is determined where the relevant likelihood and consequence intersects
Likelihood
Consequences |  | Rare Might occur but only in exceptional circumstances | Unlikely Might occur but only in unusual circumstances, strong uncertainty | Possible Might occur in certain circumstances | Likely Will probably occur in normal circumstances | Almost Certain Expected to occur in most circumstances
| Critical Loss of life or multiple loss of life to public / workers. Life threatening injury / illness to public / workers | High | High | Extreme | Extreme | Extreme
| Major One or more public / workers requiring hospitalisation and immediate medical treatment with the potential for long term incapacitation | Medium | High | High | Extreme | Extreme
| Moderate Harm, injury or illness requiring professional medical treatment for public/workers | Low | Medium | Medium | High | High
| Minor Minor harm or injury where first aid is required for public/workers | Low | Low | Medium | Medium | High
| Insignificant No harm, injuries or ailments requiring treatment to public/workers | Low | Low | Low | Medium | Medium
Risk Rating |  |  | Suggested Actions Required
Extreme |  |  | Immediate action required to manage risk
High |  |  | Urgent action required to manage risk
Medium |  |  | Action required to manage risk
Low |  |  | Risk within acceptable level*
*Although the risk is within an acceptable level, it is recommended to implement practical controls to further reduce the likelihood and/or consequence where possible
RISK ASSESSMENT ~ All columns MUST be completed
1. Hazard / Source* List individual tasks or activities |  | 2. Risks* Identify the potential risks associated with each task / activity. | 3. Risk Rating* Before Controls - Low - Medium - High - Extreme | 4. Risk Controls* Controls to address identified risks | 5. Risk Rating* After Controls - Low - Medium - High - Extreme | 6. Responsibility* Name of person responsible for implementing risk controls
Example: Food |  | Food poisoning | Medium | • Ensure all food vendors have appropriate food licences • Food vendors have adequate refrigeration / cooling for their requirements • Adequate hand washing facilities have been provided for food vendors | Low | John Smith
** Compulsory ** Mosquito Bite Mitigation (Mosquito-borne disease)
Please insert more lines if necessary
Low
Medium
High
Extreme
DECLARATION
I verify that I have, to the best of my knowledge endeavoured to anticipate all possible risks relevant to the above event and will ensure all controls listed above are implemented.
Event Organiser: |  |  |  | Organisation:
Signature: |  |  |  | Date:
Disclaimer This template has been developed as a guide only, to assist Event Organisers to identify and manage risks associated with their event. The table of example hazards, risks and controls is not exhaustive. Event Organisers must comply with all Health and Safety legislation that is applicable to the running of an event. Council accepts no legal liability for any of the information provided in your Risk Management Plan, and all risks, identified or otherwise, remain the responsibility of the Event Organiser to manage and control.

## Emergency Management
Emergency Management Plan
An Emergency Management Plan is a vital tool of event planning. This plan will outline your response in the event of a serious incident in those critical minutes before emergency services arrive to take over.
Emergency Assembly Point | Location
Assembly Area 1
Assembly Area 2
Assembly Area 3
Assembly Area 4
Communication and Coordination
Describe the communications system which will be used between organisers,staff and volunteers. Eg. Two-way radios, mobile phones etc
Describe the system to be used for communicating with the general public at your event. Eg. PA system, megaphone etc
Security and Crowd Management
Will security or crowd control be used for the event? If so, provide company details and contact information.
Traffic Management
Are any temporary road closures planned for this event? How will this be managed?
How will exhibitors, performers, staff, volunteers and emergency vehicles access the site?
Lost Persons Procedure
Detail what will happen if a lost child or person is found, where they are taken to, what staff will look after them and how will you locate their parents, guardians or friends.
Detail what will happen if a parent or guardian reports a lost child or person?
Specific Emergency Procedures
The below checklists have been provided for event organisers who do not already have a specific emergency management plan for their event. You may use these checklists (amending as necessary) at your event should an emergency occur, or you can supply your own emergency management plan.
Fire | Response actions (amend as appropriate)
Discovery of a fire | Sound fire alarm
Call 000 to notify the fire brigade
Event Coordinator or Safety Officer to meet the emergency services and direct them to the location of fire
If safe to do so extinguish fire
On sounding the alarm | If threat to life exists, Event Coordinator, Safety Officer and Area Warden will direct all persons at event to the designated assembly point(s) immediately
Walk calmly and quickly and avoiding any areas that may be a danger
Ensure attendees with disabilities are assisted
Ensure all attendees remain at the assembly point(s) until clearance to leave is given
Returning to the site | Do not return to the building/site until given the all clear by the Fire Service
Gas Leak | Response actions (amend as appropriate)
If gas leak is suspected | Evacuate immediate area
Call 000 to notify relevant Emergency Services
Event Coordinator or Safety Officer to meet the emergency services and direct them to the location of gas leak
Remove ignition sources, only if safe to do so
Isolate gas/electricity supply, only if safe to do so
If threat to life exists, sound alarm for evacuation
Event Coordinator, Safety Officer and Area Warden will direct all persons at event to the designated assembly point(s) immeditely
Walk calmly and quickly and avoiding any areas that may be a danger
Ensure all attendees remain at the evacuation point until clearance to leave is given
Returning to the site | Do not return to the building/site until given the all clear by Emergency Services
Medical Emergency | Response actions (amend as appropriate)
Incident requiring emergency medical assistance | Ensure your own safety. Assess area for danger (eg. Live wires, poisonous substances etc)
Provide first aid
Call Emergency Services on 000
Designate someone to meet the emergency services and direct them to the location of the casualty
Try not to leave the casualty until the emergency assistance arrives
Do not move casualty unless they are exposed to a life threatening situation
Extreme Weather | Response actions (amend as appropriate)
When severe storm threatens | Monitor Bureau of Meteorology website – www.bom.gov.au
Secure all items, if safe to do so
Shut off gas and electricity supply, if safe to do so
Storm approaches | Event Coordinator or Safety Officer to determine if event be cancelled
Advise all attendees of cancellation of event
On cancellation of event | Assist all attendees evacuate the site
If required and available, evacuate everyone to shelter until storm passes
Civil Disturbances | Response actions (amend as appropriate)
Disruptive person on-site | If security in attendance, notify security guard of incident and persons location
Contact Emergency Services on 000
Remain calm, do not do or say anything that will encourage irrational behaviour
If safe, move persons to predetermined safe position to await Police arrival

## COVIDSafe Event Plan
COVIDSafe Event Plan
HOW TO USE THIS TEMPLATE
Explanation
This document, when completed will provide you and other stakeholders with the information necessary to ensure your event is COVID-Safe. All sections marked with an asterisk (*) are mandatory and must be completed. If a requirement and action within each of the mandatory sections in this form is not applicable to your event, enter NOT APPLICABLE. If you require any assistance in completing your COVID-Safe Event Plan, please contact the Events Team on 5018 8100. Once this document has been completed, please submit as part of your online application. This COVID-Safe Event Plan template has been developed from the DHHS template as a guide only, to assist applicants to identify and manage COVID related risks only. Council accepts no legal liability for any of the information provided in your COVID-Safe Event Plan, and all actions, identified or otherwise, remain the responsibility of the applicant to manage and control. For further information and guidance on addressing the Six COVIDSafe Principals, please visit the Department of Health and Human Services (DHHS) website: https://www.dhhs.vic.gov.au/
Physical Distancing
You must ensure attendees are 1.5 metres apart as much as possible. This can be done by:
| Requirements | Action
• Minimising the build-up of attendees waiting to enter and exit the venue
•Using floor markings to provide minimum physical distancing guides
You should provide training to event staff on physical distancing expectations while working and socialising. This should include:
| Requirements | Action
•Informing event staff to follow current public health directions at all times. This can be found at www.dhhs.vic.gov.au
• Ensure appropriate training has been provided to event staff, should staff be subjected to negative public response (aggressive/negative behaviour) in relation to COVID Safe Requests.
Wear a Face Covering
It is recommended that individuals aged 12 years and over wear a face covering/mask where you are unable to physically distance, in accordance with public health advice. https://www.coronavirus.vic.gov.au/face-masks-when-wear-face-mask
| Requirements | Action
• Providing adequate face coverings and Personal Protective Equipment (PPE) to event staff and attendees that do not have their own (where required)
•You should provide training, instruction and guidance on how to correctly fit, use and dispose of PPE. You should inform events staff that cloth masks should be washed each day after use. However, if during the day the mask is visibly dirty or wet, the mask needs to be washed immediately
Practise Good Hygiene
You must frequently and regularly clean and disinfect shared spaces, including high-touch communal items such as door handles, tables and chairs.
| Requirements | Action
You should: •Clean surfaces with appropriate cleaning products, including detergent and disinfectant single-use or contactless options whilst wearing gloves and adequate PPE. Dispose of used cleaning items in a contained and hygienic manner after each use. (i.e. designated rubbish/disposal bins)
• Replace high-touch communal items with hygienic alternatives, for example: - Clean between shifts, where possible to do so - You should display a cleaning log in shared spaces
• You should make soap and hand sanitiser available for all staff and attendees throughout the event and encourage regular handwashing
Keep Records and Act Quickly if Event Staff and Attendees Become Unwell
| Requirements | Action
• You must support any event staff and attendees to get tested and stay home even if they only have mild symptoms
| Requirements | Action
• Having a plan to respond to event staff being notified they are a positive case during the event
• Having a plan to identify and notify close contacts in the event of a positive case attending the event during their infectious period
• Having a plan to notify DHHS if you have a confirmed COVID-19 case at your event. Following notification to DHHS, you must then contact your Council representative who will notify Worksafe Victoria. https://www.worksafe.vic.gov.au/notifiable-incidents-involving-coronavirus-covid-19
• Having a plan in place to clean the venue (or part) in the event of a positive case
• Having a plan to contact DHHS and notify the actions taken, provide a copy of the risk assessment conducted and contact details of any close contacts
• Having a plan in the event that you have been instructed to close the event by DHHS
• You must keep records of all people who attended the event for contact tracing. The Victorian Government has implemented a free QR code service and can be utilised by visiting https://www.coronavirus.vic.gov.au/register-for-qr-code to register to use the Victorian Government QR Code Service
Create Event Workforce Bubbles
| Requirements | Action
• You should keep groups of event staff rostered on the same shifts at a single venue and ensure there is no overlap of staff during shift changes
• You should maintain records of all event staff who have disclosed that they reside with another staff member and ensure that there is no cross-over between shifts
DECLARATION
I verify that I have, to the best of my knowledge endeavoured to anticipate all possible COVID related risks relevant to the event activities and will ensure all actions listed above are implemented, including the verification of event staff and attendee vaccination status.
| Event Organiser: | Organisation:
| Signature: | Date:
Disclaimer This template has been developed as a guide only, to assist applicants to identify and manage COVID related risks associated with their event activities. Council accepts no legal liability for any of the information provided in your COVID-Safe Event Plan, and all actions, identified or otherwise, remain the responsibility of the applicant to manage and control.

## Incident Report Form
Incident Report & Investigation Form
Use this incident report & investigation form to record any incidents, near misses, injuries, potential injuries or damage to property that occur during your event, including bump in and bump out.
REPORT SECTION
To be completed within 12 hours of incident occuring / event concluding
This is a report of: (Please tick one only)
|  | Injury to an employee (First Aid treatment) |  |  |  |  | Complete sections 1, 2, 3, 4, 6, 10
|  | Injury to an employee (Medical treatment ) |  |  |  |  | Complete sections 1, 2, 3, 5, 6, 10
|  | Hazard |  |  |  |  | Complete sections 2, 7, 10
|  | Incident – no injury or damage (eg near miss) |  |  |  |  | Complete sections 2, 3, 10
|  | Injury to Third Party (eg member of the public) |  |  |  |  | Complete sections 1, 2, 3, 4, 5, 6, 10
|  | Damage to Third Party property |  |  |  |  | Complete sections 2, 3, 8, 9, 10
|  | Vehicle/Machine damage |  |  |  |  | Complete sections 2, 3, 8, 9, 10
1. Details of injured person
| Name: | [6 empty] | Date of Birth:
Postal Address:
|  | Employee |  | Position:
|  | Third Party |  | Phone:
| Lost time Injury |  | Yes | No |  | Date & Time Ceased Work:
2. Details of person completing form (if the same as section 1, enter "As above")
| Name: | [6 empty] | Phone:
Relationship to the injured person:
3. Incident Details
| Incident Date: | [7 empty] | Time:
| Reported to: | [7 empty] | Date & Time:
| Where did the incident occur? |  |  |  | Mildura Rural City Council property |  |  |  |  | Other Location
Where was the exact location:
| Did Emergency Services attend? |  |  |  | Yes | No | Police | Ambulance |  | Fire Brigade
What was the person doing at the time leading up to the incident?
Provide details of what happened & any injuries
| Name of Witness: | [8 empty] | Phone:
Tick the box(es) that best describe the type of incident:
|  | Fall to same level |  |  |  | Exposure to noise/pressure/vibration |  |  |  | Exposure to cold/heat/radiation
|  | Fall to different level |  |  |  | Sudden loud noise |  |  |  | Exposure to chemicals, dust or gas
|  | Strike against/stepped on |  |  |  | Lifting |  |  |  | Biological exposure
|  | Hit by object |  |  |  | Pushing |  |  |  | Mental stress
|  | Hit against object |  |  |  | Pulling |  |  |  | Contact with vermin, insects etc
|  | Caught in/between object |  |  |  | Prolonged work in one position |  |  |  | Other (please specify)
|  | Motor vehicle accident |  |  |  | Stretching/over-reaching
|  | Electric shock |  |  |  | Twisting
|  | Act of aggression by other person |  |  |  | Prolonged repetitive movement
Tick the box(es) that best describe the weather at the time of the incident:
|  | Indoor Incident |  |  |  | Outdoor Incident |  |  |  | Temperature <30 C
|  | Sunny |  |  |  | Raining |  |  |  | Temperature >30 C
|  | Overcast |  |  |  | Humid |  |  |  | Other:
|  | Windy |  |  |  | Dusty
In your opinion, what was the cause of the incident?
In your opinion, what can be done to prevent this type of incident re-occurring?
4. First Aid Details
| Name of person providing first aid: | [8 empty] | Phone:
Details of first aid treatment given:
5. Medical Treatment
| Name of doctor: | [7 empty] | Date & Time:
| Name of Hospital: | [7 empty] | Date & Time:
6. Injury Details
| Body Injury Location: |  |  | Left |  |  | Right
|  | Head |  | Arm |  |  | Leg |  |  | Internal System
|  | Eye |  | Shoulder |  |  | Knee |  |  | Psychological
|  | Neck |  | Elbow |  |  | Ankle |  |  | Other (please specify)
|  | Torso |  | Wrist |  |  | Foot
|  | Back |  | Hand |  |  | Toe
|  | Groin |  | Finger/Thumb |  |  | Multiple
Nature of injury:
|  | Sprain/Strain |  |  | Abrasion/Laceration |  |  | Burn/Scald |  |  | Bite - from insect
|  | Bruise/Swelling |  |  | Puncture wound |  |  | Electric Shock |  |  | Bite - from animal
|  | Dislocation |  |  | Foreign body |  |  | Crush |  |  | Bite - from human
|  | Concussion |  |  | Amputation |  |  | Allergic reaction |  |  | Other (please specify)
|  | Deafness |  |  | Fracture |  |  | Infection/Infestation
7. Hazard Details
What is the hazard?
What can be or has been done to eliminate or control the hazard?
8. Property Damage Details
| Name of Property Owner: | [8 empty] | Phone:
Property Address:
Type of Property:
What is the exact loation of the damaged property?
| Estimated Cost of repairs: |  |  | $
What were the weather conditions?
Give a detailed description of the damage:
9. Environmental Damage Details
Specify the effect on the environment:
Who was directly affected?
| Was the Environmental Protection Authority notified? | [5 empty] | Yes | No | Date & Time:
| Was Workcover notified? | [5 empty] | Yes | No | Date & Time:
| Did you inform the Environmental Health Officer? | [5 empty] | Yes | No | Date & Time:
INVESTIGATION SECTION
This section is to be completed by the Event Coordinator within 24 hours of incident occuring / event concluding
1. Contributing Factors
What do you consider were the main contributing factors to this incident/hazard? (More than one box may be ticked)
| Procedures: | [6 empty] | Work Environment:
|  | Employee not aware of correct procedure | [6 empty] | Inappropriate workplace design
|  | Employee was aware but failed to follow correct procedure | [6 empty] | Inappropriate task allocation (eg in RSI)
|  | Procedure followed, but was inappropriate to condition | [6 empty] | Poor housekeeping
|  | No formal procedure in place | [5 empty] | External Influence:
| Equipment: | [7 empty] | Incident caused by another person or thing
|  | Appropriate equipment available but not used | [6 empty] | Weather conditions
|  | Appropriate equipment not supplied | [5 empty] | Training:
|  | Equipment failure/malfunction | [6 empty] | Employee not adequately trained
|  | Equipment not properly repaired/maintained | [6 empty] | Supervisor not adequately trained
|  | Equipment not used correctly | [5 empty] | Action by Employee:
|  | Equipment not appropriate for the task | [6 empty] | Employee performed unsafe act
2. Risk Assessment
| 1. What is the Consequence of this happening? (1, 2, 3, 4, 5) | [5 empty] | CONSEQUENCE
[7 empty] | LIKELIHOOD |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04
| 2. What is the Likelihood of this happening? (A, B, C, D, E) | [6 empty] | A | M | M | H | H | E
[8 empty] | B | L | M | M | H | E
| 3. On the matrix this equates to a Risk Factor of (L, M, H, E) | [6 empty] | C | L | L | M | H | H
[8 empty] | D | L | L | M | M | H
[8 empty] | E | L | L | L | M | M
| Consequence 5 Catastrophic Death, huge financial loss, irreversible damage 4 Major Extensive injuries, major financial loss 3 Moderate Medical treatment required, high financial loss 2 Minor First aid treatment required, low financial loss 1 Negligible Minor first aid, minimal financial loss | [6 empty] | Likelihood A Almost Certain Will occur in most circumstances B Likely Will probably occur in most circumstances C Possible Might occur at some time D Unlikely Could occur at some time E Rare May occur in exceptional circumstances
| E = EXTREME RISK Immediate action required – STOP WORK/TAG OUT | [6 empty] | H = HIGH RISK Senior management attention needed
| M = MODERATE RISK Management responsibility to be allocated | [6 empty] | L = LOW RISK Manage through usual/routine processes
3. Risk Control
Risk Factor Rating: (Extreme, High, Moderate, Low)
The Hierarchy of Control is a list of control measures, in priority order, that can be used to eliminate or minimise exposure to hazards. Application of the Hierarchy of Control measures involves firstly assessing whether the risk/hazard can be eliminated. Where this is not practicable, substitution should be considered. If this is not practicable, consideration should be given to each of the other control measures – isolation, engineering controls, administrative control/safe work practices, and use of PPE – in turn, until a control measure or combination of control measures are identified which can achieve the required reduction in exposure.
| SAFE PLACE SAFE PERSON |  | 1. Eliminate |  |  | Remove risk from the process by eliminating the step in the process, or eliminating the hazard
|  |  | 2. Substitute/Avoid |  |  | Consider whether the process or activity is required, or whether another process or activity can be substituted (eg. Use a water based paint)
|  |  | 3. Isolation |  |  | Removing or seperating people from the source of the hazard. Consider physical barriers such as fencing, abrricading or distance.
|  |  | 4. Engineering Control |  |  | Changing the physical characteristics of plant or workplace to remove or reduce the risk (eg. Machine guarding, using mechanical aids, reversing beepers, etc)
|  |  | 5. Administration Control |  |  | Use of policies, procedures for safe work practices, signs, training, job rotation, etc to control risk
|  |  | 6. Personal Protective Equipment |  |  | Employee is required to use/wear PPE (eg. Safety glasses, gloves, hearing protection, red safety vest, hard helmet, safety boots etc)
Using the 'Hierarchy of Control' above, what have you done to eliminate the hazard/prevent this type of incident occurring again? Please complete the questions below in full prior to developing your agreed corrective action/s:
| 1. Is Elimination of the risk/hazard possible? |  |  |  |  | Yes - How? |  | No - Why not?
| 2. Is there a Substitution available that would eliminate the risk/hazard? | [6 empty] | Yes - How? |  | No - Why not? |  | N/A
| 3. Is Isolution of the risk/hazard possible? | [6 empty] | Yes - How? |  | No - Why not? |  | N/A
| 4. Is an Engineering Control of the risk/hazard possible? | [6 empty] | Yes - How? |  | No - Why not? |  | N/A
| 5. Is an Administrative Control available that would eliminate the risk/hazard? | [6 empty] | Yes - How? |  | No - Why not? |  | N/A
| 6. Is PPE of the risk/hazard possible? | [6 empty] | Yes - How? |  | No - Why not? |  | N/A
4. Corrective Action/s
What action/s or control/s have been implemented/completed?
Date Implemented:
or
If nothing has been done as yet, what will you do to eliminate the hazard/prevent this type of incident occurring again?
Who will carry out this action?
By when will the action be carried out?
Risk rating with control/s in place:
1. What is the Consequence of this happening? (1, 2, 3, 4, 5)
2. What is the Likelihood of this happening? (A, B, C, D, E)
3. On the matrix this equates to a Risk Factor of (L, M, H, E)
| If a Manual Handling incident, has a Manual Handling Hazard ID, Risk been completed? | [7 empty] | Yes | No
| Copy of Manual Handling Assessment attached? | [7 empty] | Yes | No
5. Investigator's Signature
| Name: | [6 empty] | Phone:
| Signature: | [6 empty] | Date: